## Summary per Organisation
ORIGINAL BUDGET MARCH 2016
| 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL ORIGINAL
| Budget | Budget | Budget | Budget | Budget
Simavi | 861470 | 695887 | 764226 | 521087 | 556635 | 3399305
Solidaridad | 639243 | 754897 | 546739 | 525120 | 530994 | 2996993
Healthy Entrepreneurs | 736273 | 742936 | 40000 | 40000 | 40000 | 1599209
TOTAL | 2236986 | 2193720 | 1350965 | 1086207 | 1127629 | 7995507
| REVISED BUDGET JUNE 2020 | AUDITED EXPENDITURES | [5 empty] | Variance
| 2016-2020 | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL EXPENSES
|  | Audited | Audited | Audited | Audited | Audited
Simavi | 3472305.2965 | 375703 | 1055469 | 696820 | 645861.3 | 690195.81 | 3464049.11 | 8256.1865
Solidaridad | 2928992.88 | 397472 | 630764 | 753995 | 598021.88 | 547654 | 2927906.88 | 1086
Healthy Entrepreneurs | 1594208.9778 | 537086 | 800993 | 166911 | 41981.9778 | 47365.152 | 1594337.1298 | -128.152
TOTAL | 7995507.1544 | 1310261 | 2487226 | 1617726 | 1285865.1578 | 1285214.962 | 7986293.1198 | 9214.0345

## GOLDEN LINE CONSOLIDATED
CONSOLIDATED
Project Title: THE GOLDEN LINE
Current Reporting Period: January 2016 to December 2019
Reporting Currency: EURO
|  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  | 2020 |  |  |  | TOTAL GOLDEN LINE
BUDGET LINE |  | Approved Original Budget | Audited Expenditures | Variance 2016 |  | Approved Revised Budget | Audited Expenditures | Variance 2017 |  | Approved Revised Budget | Audited Expenditures | Variance 2018 |  | Approved Revised Budget | Audited Expenditures | Variance 2019 | Audited Expenditures | Audited Expenditures | Variance 2020 |  | Total ORIGINAL Budget 2016-2020 | Audited Expenditures 2016-2020 | Variance 2016 -2020 (Original budget versus expenditures) | % burn rate
Outcome 1: Women have improved working conditions within gold mines |  | 431070 | 251032 | 180038 | 0 | 769918 | 418976.6 | 350941.4 | 0 | 512781 | 543848 | -31067 | 0 | 579469 | 402360.6 | 177108.4 | 399262 | 433352 | -34090 | 0
1.1.1 | # ASG miners that aligned their policies with the FT/FM in support of women's needs and rights | 31000 | 11557 | 19443 | 0
1.1.2 | # ASG miners that adapted operational procedures in line with FT/FM in support of women's needs and rights | 206320 | 94122 | 112198 | 0
1.2.1 | Assessments of local and national policies conducted | 42750 | 53741 | -10991 | 0
1.2.2 | # local or national gender sensitive ASGM policies being developed | 7250 | 0 | 7250 | 0
1.2.3 | # local or national gender sensitive ASGM policies finalised and approved | 23000 | 11314 | 11686 | 0
1.3.1 | # of gold buyers with secured sourcing commitments for gold produced in the project | 71000 | 34646 | 36354 | 0
1.3.2 | # of market players that have attended meetings or received information about responsible gold in support of women's needs and rights | 24200 | 20100 | 4100 | 0
1.4.1 | # of new credit products available to ASG miners | 12775 | 12776 | -1 | 0
1.4.2 | # of ASG miners that use new financial instruments for ASGMS | 12775 | 12776 | -1 | 0
|  | 0 | 0 | 0 | 0
1.1 Gold mines operate according to fair mining practices in support of women's needs and rights |  | 0 | 0 | 0 | 0 | 390462 | 215854 | 174608 | 0 | 145533 | 257846 | -112313 |  | 177255 | 178350 | -1095 | 159369 | 143956 | 15413
1.2 Gender-sensitive ASG mining policies are in place at local and national levels |  | 0 | 0 | 0 | 0 | 114106 | 63975 | 50131 | 0 | 111055 | 151384 | -40329 |  | 96966 | 79817.6 | 17148.4 | 61300 | 64543 | -3243
1. 3 Market players demand responsible gold in support of women's needs and rights |  | 0 | 0 | 0 | 0 | 121700 | 54545 | 67155 | 0 | 141000 | 33698 | 107302 |  | 197630 | 47074 | 150556 | 75500 | 139256 | -63756
1.4 ASG mines have access to credit to implement fair mining practices |  | 0 | 0 | 0 | 0 | 25500 | 3592.6 | 21907.4 | 0 | 42304 | 10680 | 31624 |  | 54506 | 37376 | 17130 | 9999 | 0 | 9999
1. 5 Women in mines have improved positions | Women in mines have improved positions | 0 | 0 | 0 | 0 | 118150 | 81010 | 37140 | 0 | 72889 | 90240 | -17351 |  | 53112 | 59743 | -6631 | 93094 | 85597 | 7497
1.1.0 Objective 1 Supporting costs | Objective 1 Supporting costs | 69070 | 60104.8104 | 8965.1896 | 0 | 58317 | 52372.5 | 5944.5 | 0 | 88147 | 105303.1341 | -17156.1341 |  | 79542 | 101195.9447 | -21653.9447 | 86340 | 85995 | 345
| TOTAL OUTCOME 1 | 500140 | 311136.8104 | 189003.1896 | 0 | 828235 | 471349.1 | 356885.9 | 0 | 600928 | 649151.1341 | -48223.1341 |  | 659011 | 503556.5447 | 155454.4553 | 485602 | 519347 | -33745 |  | 2393074 | 2454540.5893 | -61466.5893 | 102.6%
Outcome 2: Women in mining communities have increased abilities to engage in economic activities |  | 1024273 | 472999.66 | 551273.34 | 0 | 1562595.1 | 1300121.92 | 262473.18 | 0 | 488350.9728 | 489000.52 | -649.5472 |  | 239600 | 226173.0178 | 13426.9822 | 248987 | 256178 | -7191
2.1.1 | % of women that have adopted healthier behaviour in their daily lives (use of contraceptives, MHM, ANC,..) | 173000 | 93727.73 | 79272.27 | 0
2.1.2 | % of SRH facilities that increased their compliance to the (national) quality standard in the intervention areas | 116000 | 82500 | 33500 | 0
2.2.1 | % of women that indicate to have more time available to spend on economic activities | 328500 | 176239.64 | 152260.36 | 0
2.2.2 | % community acceptance on women to decide on family planning | 229631 | 99450.29 | 130180.71 | 0
2.2.3 | % of women who feel more productive during their periods | 52142 | 21082 | 31060 | 0
2.3.1 | Acceptance in the community for women to co-decide on family planning | 75000 | 0 | 75000 | 0
2.3.2 | % community leaders that have demonstrated to be supportive to equal opportunities for women | 50000 | 0 | 50000 | 0
|  | 0 | 0 | 0 | 0
2.1 Women in mining communities have improved SRHR |  | 0 | 0 | 0 | 0 | 489855.7 | 442350.0672 | 47505.6328 | 0 | 151998 | 173114.6823 | -21116.6823 | 0 | 65900 | 62816.688 | 3083.312 | 86836.2 | 90863 | -4026.8
2.2 Mining communities, especially men, recognise the importance of gender equality |  | 0 | 0 | 0 | 0 | 702154.4 | 579386.1399 | 122768.2601 | 0 | 108852 | 114026.3235 | -5174.3235 | 0 | 53766.6667 | 50616.7351 | 3149.9315 | 50950 | 50990 | -40
2.3 Effective national lobby for women-friendly health services | Effective national lobby for women-friendly health services | 0 | 0 | 0 | 0 | 112600 | 56272.5 | 56327.5 | 0 | 95416.9728 | 51859 | 43557.9728 | 0 | 30433.3333 | 28576.3258 | 1857.0075 | 32627 | 32555 | 72
2.4 Women have increased access to and control over resources | Women have increased access to and control over resourcess | 0 | 0 | 0 | 0 | 257985 | 222113.2129 | 35871.7871 | 0 | 132084 | 150000.5143 | -17916.5143 | 0 | 89500 | 84163.2688 | 5336.7312 | 78573.8 | 81770 | -3196.2
2.2.0 Objective 2 Supporting costs | Objective 1 Supporting costs | 145200 | 98866.6435 | 46333.3565 | 0 | 125546 | 121881.5 | 3664.5 | 0 | 183900 | 146531.31 | 37368.69 | 0 | 127534 | 163101.4753 | -35567.4753 | 147512.5 | 141242 | 6270.5
| TOTAL OUTCOME 2 | 1169473 | 571866.3035 | 597606.6965 | 0 | 1688141.1 | 1422003.42 | 266137.68 | 0 | 672250.9728 | 635531.83 | 36719.1428 | 0 | 367134 | 389274.4931 | -22140.4931 | 396499.5 | 397420 | -920.5 |  | 3394333 | 3416096.0466 | -21763.0466 | 100.6%
3.1.0 Monitoring and Evaluation |  | 115390 | 75822.8 | 39567.2 | 0 | 15000 | 134373.05 | -119373.05 | 0 | 0 | 0 | 0 | 0 | 95000 | 94469.53 | 530.47 | 109000 | 109479.5178 | -479.5178
3.2.0 PME Supporting costs | M&E including external evaluators / auditors | 42200 | 39546.5437 | 2653.4563 | 0 | 28790 | 46872 | -18082 | 0 | 27011.763 | 37251 | -10239.237 | 0 | 34170 | 32058.8 | 2111.2 | 38656.3445 | 35627.84 | 3028.5045
| TOTAL PME COSTS | 157590 | 115369.3437 | 42220.6563 | 0 | 43790 | 181245.05 | -137455.05 | 0 | 27011.763 | 37251 | -10239.237 | 0 | 129170 | 126528.33 | 2641.67 | 147656.3445 | 145107.3578 | 2548.9866 |  | 455030 | 605501.0815 | -150471.0815 | 133.1%
3.3.0 CSO capacity building |  | 46000 | 33372 | 12628 | 0 | 45000 | 72792 | -27792 | 0 | 46000 | 33771.36 | 12228.64 | 0 | 25000 | 10450.82 | 14549.18 | 20500 | 19779.24 | 720.76
3.3.1 CSO capacity building supporting costs | M&E including external evaluators / auditors | 46000 | 33373 | 12627 | 0 | 47948 | 42873.19 | 5074.81 | 0 | 17306.44 | 22878.75 | -5572.31 | 0 | 11986 | 13399.8 | -1413.8 | 10131.0176 | 10881.56 | -750.5424
| TOTAL CSO CAPACITY BUILDING COSTS | 92000 | 66745 | 25255 | 0 | 92948 | 115665.19 | -22717.19 | 0 | 63306.44 | 56650.11 | 6656.33 | 0 | 36986 | 23850.62 | 13135.38 | 30631.0176 | 30660.8 | -29.7824 |  | 288871 | 293571.72 | -4700.72 | 101.6%
3.4.0 Programme support The Netherlands | M&E including external evaluators / auditors | 317783 | 245144.11 | 72638.89 | 0 | 365381.1 | 296962.65 | 68418.45 | 0 | 331874.7895 | 239141.33 | 92733.4595 | 0 | 250184 | 242655.17 | 7528.83 | 234040.1344 | 192680.235 | 41359.8994 |  | 1464200 | 1216583.495 | 247616.505 | 83.09%
| TOTAL OTHER COSTS | 567373 | 427258.4537 | 140114.5463 | 0 | 502119.1 | 593872.89 | -91753.79 | 0 | 422192.9925 | 333042.44 | 89150.5525 | 0 | 416340 | 393034.12 | 23305.88 | 412327.4965 | 368448.3928 | 43879.1037 |  | 2208101 | 2115656.2965 | 92444.7035 | 95.81%
[16 empty] | 0 |  |  | 0 |  |  | 0
| GRAND TOTAL | 2236986 | 1310261.5676 | 926724.4324 | 0 | 3018495.2 | 2487225.41 | 531269.79 | 0 | 1695371.9653 | 1617725.4041 | 77646.5612 | 0 | 1442485 | 1285865.1578 | 156619.8422 | 1294428.9965 | 1285215.3928 | 9213.6037 |  | 7995508 | 7986292.9324 | 9215.0676 | 99.88%
| ORIGINAL GRAND TOTAL BUDGET MARCH 2016 | 2236986 |  |  |  | 2193720 |  |  |  | 1350965 |  |  |  | 1086207 |  |  | 1127629 |  |  |  | 7995507

## Ghana
GHANA
Project Title: THE GOLDEN LINE
Current Reporting Period: January 2016 to December 2019
Reporting Currency: EURO
|  | 2016 GHANA |  |  |  | 2017 GHANA |  |  |  | 2018 GHANA |  |  |  | 2019 GHANA |  |  |  | 2020 GHANA |  |  |  | TOTAL GHANA
BUDGET LINE |  | Approved Original Budget | Audited Expenditures | Variance 2016 |  | Approved Revised Budget | Audited Expenditures | Variance 2017 |  | Approved Revised Budget | Audited Expenditures | Variance 2018 |  | Approved Revised Budget | Audited Expenditures | Variance 2019 |  | Approved Revised Budget | Audited Expenditures | Variance 2020 |  | Total ORIGINAL Budget 2016-2020 | Audited Expenditures 2016-2020 | Variance 2016 -2020 (Original budget versus expenditures) | % bun rate
Outcome 1: Women have improved working conditions within gold mines |  | 196100 | 139974 | 56126 | 0 | 301540 | 150525.8 | 151014.2 | 0 | 261469 | 212637.5 | 48831.5 | 0 | 313776 | 197422.3 | 116353.7 | 0 | 205687 | 230869 | -25182 | 0
1.1.1 | # ASG miners that aligned their policies with the FT/FM in support of women's needs and rights | 16000 | 2903 | 13097
1.1.2 | # ASG miners that adapted operational procedures in line with FT/FM in support of women's needs and rights | 83100 | 45160 | 37940
1.2.1 | Assessments of local and national policies conducted | 21000 | 43110 | -22110
1.2.2 | # local or national gender sensitive ASGM policies being developed | 3625 | 0 | 3625
1.2.3 | # local or national gender sensitive ASGM policies finalised and approved | 12000 | 8652 | 3348
1.3.1 | # of gold buyers with secured sourcing commitments for gold produced in the project | 35500 | 17323 | 18177
1.3.2 | # of market players that have attended meetings or received information about responsible gold in support of women's needs and rights | 12100 | 10050 | 2050
1.4.1 | # of new credit products available to ASG miners | 6387.5 | 6388 | -0.5
1.4.2 | # of ASG miners that use new financial instruments for ASGMS | 6387.5 | 6388 | -0.5
1.1 Gold mines operate according to fair mining practices in support of women's needs and rights |  | 0 | 0 | 0 | 0 | 156838 | 71996 | 84842 | 0 | 91000 | 90997 | 3 | 0 | 113000 | 95374 | 17626 | 0 | 79250 | 79207 | 43 | 0
1.2 Gender-sensitive ASG mining policies are in place at local and national levels |  | 0 | 0 | 0 | 0 | 58102 | 34089 | 24013 | 0 | 59750 | 65990.5 | -6240.5 | 0 | 49708 | 35817.3 | 13890.7 | 0 | 25000 | 34914 | -9914 | 0
1. 3 Market players demand responsible gold in support of women's needs and rights |  | 0 | 0 | 0 | 0 | 60850 | 27272.5 | 33577.5 | 0 | 70500 | 16849 | 53651 | 0 | 98815 | 23537 | 75278 | 0 | 44444.5 | 69628 | -25183.5 | 0
1.4 ASG mines have access to credit to implement fair mining practices |  | 0 | 0 | 0 |  | 12750 | 1796.3 | 10953.7 |  | 21152 | 5340 | 15812 |  | 27253 | 18688 | 8565 |  | 9999.5 | 0 | 9999.5
1. 5 Women in mines have improved positions | Women in mines have improved positions | 0 | 0 | 0 |  | 13000 | 15372 | -2372 |  | 19067 | 33461 | -14394 |  | 25000 | 24006 | 994 |  | 46993 | 47120 | -127
1.1.0 Objective 1 Supporting costs | Objective 1 Supporting costs | 41510 | 38207.6643 | 3302.3357 |  | 28908 | 29212 | -304 |  | 37923.5 | 42832.7775 | -4909.2775 |  | 32910 | 43462.3587 | -10552.3587 |  | 35267.4 | 33878 | 1389.4
| TOTAL OUTCOME 1 | 237610 | 178181.6643 | 59428.3357 |  | 330448 | 179737.8 | 150710.2 |  | 299392.5 | 255470.2775 | 43922.2225 |  | 346686 | 240884.6587 | 105801.3413 |  | 240954.4 | 264747 | -23792.6 |  | 1128311 | 1119021.4005 | 9289.5995 | 99.18%
Outcome 2: Women in mining communities have increased abilities to engage in economic activities |  | 538082 | 232700.7 | 305381.3 |  | 843131.7 | 766268.92 | 76862.78 |  | 250489.5864 | 194838 | 55651.5864 |  | 132800 | 111006.7105 | 21793.2895 |  | 140134 | 160103 | -19969
2.1.1 | % of women that have adopted healthier behaviour in their daily lives (use of contraceptives, MHM, ANC,..) | 87000 | 35496 | 51504 | [11 empty] | 0 |  |  |  | 0
2.1.2 | % of SRH facilities that increased their compliance to the (national) quality standard in the intervention areas | 63000 | 35700 | 27300 | [11 empty] | 0 |  |  |  | 0
2.2.1 | % of women that indicate to have more time available to spend on economic activities | 171000 | 97564.7 | 73435.3 | [11 empty] | 0 |  |  |  | 0
2.2.2 | % community acceptance on women to decide on family planning | 120440 | 52138 | 68302 | [11 empty] | 0 |  |  |  | 0
2.2.3 | % of women who feel more productive during their periods | 26642 | 11802 | 14840 | [11 empty] | 0 |  |  |  | 0
2.3.1 | Acceptance in the community for women to co-decide on family planning | 40000 | 0 | 40000 | [11 empty] | 0 |  |  |  | 0
2.3.2 | % community leaders that have demonstrated to be supportive to equal opportunities for women | 30000 | 0 | 30000 | [11 empty] | 0 |  |  |  | 0
[16 empty] | 0 |  |  |  | 0
2.1 Women in mining communities have improved SRHR |  | 0 | 0 | 0 |  | 287133.7 | 293727.995 | -6594.295 |  | 79431 | 71378.1903 | 8052.8097 |  | 34600 | 28731.9511 | 5868.0489 |  | 53661.2 | 61231 | -7569.8
2.2 Mining communities, especially men, recognise the importance of gender equality |  | 0 | 0 | 0 |  | 362233 | 313113.195 | 49119.805 |  | 52042 | 41500.0079 | 10541.9921 |  | 30800 | 25560.6813 | 5239.3187 |  | 23975 | 27001 | -3026
2.3 Effective national lobby for women-friendly health services | Effective national lobby for women-friendly health services | 0 | 0 | 0 |  | 59120 | 24489.2 | 34630.8 |  | 46153.5864 | 24716 | 21437.5864 |  | 17400 | 15100.5359 | 2299.4641 |  | 14899 | 17313 | -2414
2.4 Women have increased access to and control over resources | Women have increased access to and control over resourcess | 0 | 0 | 0 |  | 134645 | 134938.53 | -293.53 |  | 72863 | 57243.8018 | 15619.1982 |  | 50000 | 41613.5422 | 8386.4578 |  | 47598.8 | 54558 | -6959.2
2.2.0 Objective 2 Supporting costs | Objective 1 Supporting costs | 74400 | 51841 | 22559 |  | 63173 | 60596.83 | 2576.17 |  | 84900 | 65482.8 | 19417.2 |  | 55817 | 80536.5613 | -24719.5613 |  | 70408.6 | 62678 | 7730.6
| TOTAL OUTCOME 2 | 612482 | 284541.7 | 327940.3 |  | 906304.7 | 826865.75 | 79438.95 |  | 335389.5864 | 260320.8 | 75068.7864 |  | 188617 | 191543.2717 | -2926.2717 |  | 210542.6 | 222781 | -12238.4 |  | 1801136 | 1786052.5217 | 15083.4783 | 99.16%
[16 empty] | 0 |  |  |  | 0
3.1.0 Monitoring and Evaluation |  | 58050 | 37896.25 | 20153.75 |  | 7500 | 98794.55 | -91294.55 |  | 0 | 0 | 0 |  | 47500 | 47651.03 | -151.03 |  | 53000 | 53307.5178 | -307.5178
3.2.0 PME Supporting costs | M&E including external evaluators / auditors | 22300 | 24406.4571 | -2106.4571 |  | 14095.5 | 19300 | -5204.5 |  | 11178.8815 | 16303 | -5124.1185 |  | 16610 | 13468.4 | 3141.6 |  | 17005.1722 | 15523.84 | 1481.3322
| TOTAL PME COSTS | 80350 | 62302.7071 | 18047.2929 |  | 21595.5 | 118094.55 | -96499.05 |  | 11178.8815 | 16303 | -5124.1185 |  | 64110 | 61119.43 | 2990.57 |  | 70005.1722 | 68831.3578 | 1173.8144 |  | 229070 | 326651.045 | -97581.045 | 142.6%
3.3.0 CSO capacity building |  | 23300 | 21995 | 1305 |  | 21000 | 37257 | -16257 |  | 25500 | 18414.84 | 7085.16 |  | 14500 | 6950.82 | 7549.18 |  | 14000 | 14172.24 | -172.24
3.3.1 CSO capacity building supporting costs | M&E including external evaluators / auditors | 23300 | 21996 | 1304 |  | 27574 | 26148.28 | 1425.72 |  | 8653.22 | 13262.75 | -4609.53 |  | 5993 | 6653.4 | -660.4 |  | 5065.5088 | 5586.56 | -521.0512
| TOTAL CSO CAPACITY BUILDING COSTS | 46600 | 43991 | 2609 |  | 48574 | 63405.28 | -14831.28 |  | 34153.22 | 31677.59 | 2475.63 |  | 20493 | 13604.22 | 6888.78 |  | 19065.5088 | 19758.8 | -693.2912 |  | 148285 | 172436.89 | -24151.89 | 116.3%
3.4.0 Programme support The Netherlands | M&E including external evaluators / auditors | 160041 | 124070 | 35971 |  | 185008.05 | 148481.325 | 36526.725 |  | 167921 | 119570.665 | 48350.335 |  | 126242 | 121327.585 | 4914.415 |  | 113175.5672 | 102473.235 | 10702.3322 |  | 733860 | 615922.81 | 117937.19 | 83.93%
| TOTAL OTHER COSTS | 286991 | 230363.7071 | 56627.2929 |  | 255177.55 | 329981.155 | -74803.605 |  | 213253.1015 | 167551.255 | 45701.8465 |  | 210845 | 196051.235 | 14793.765 |  | 202246.2483 | 191063.3928 | 11182.8554 |  | 1111215 | 1115010.745 | -3795.745 | 100.3%
[16 empty] | 0 |  |  |  | 0 |  |  | 0
| GRAND TOTAL | 1137083 | 693087.0714 | 443995.9286 |  | 1491930.25 | 1336584.705 | 155345.545 |  | 848035.1879 | 683342.3325 | 164692.8554 |  | 746148 | 628479.1655 | 117668.8345 |  | 653743.2483 | 678591.3928 | -24848.1446 |  | 4040662 | 4020084.6672 | 20577.3328 | 99.49%

## Tanzania
TANZANIA
Project Title: THE GOLDEN LINE
Current Reporting Period: January 2016 to December 2019
Reporting Currency: EURO
|  | 2016 TANZANIA |  |  |  | 2017 TANZANIA |  |  |  | 2018 TANZANIA |  |  |  | 2019 TANZANIA |  |  |  | 2020 TANZANIA |  |  |  | TOTAL TANZANIA
BUDGET LINE |  | Approved Original Budget | Audited Expenditures | Variance 2016 |  | Approved Revised Budget | Audited Expenditures | Variance 2017 |  | Approved Revised Budget | Audited Expenditures | Variance 2018 |  | Approved Revised Budget | Audited Expenditures | Variance 2019 |  | Approved Revised Budget | Audited Expenditures | Variance 2020 |  | Total ORIGINAL Budget 2016-2020 | Audited Expenditures | Variance 2016 -2020 (Original budget versus expenditures) | % burn rate
Outcome 1: Women have improved working conditions within gold mines |  | 234970 | 111058 | 123912 | 0 | 468378 | 268450.8 | 199927.2 | 0 | 251312 | 331210.5 | -79898.5 | 0 | 265693 | 204938.3 | 94691.18 | 0 | 193575 | 202483 | -8908 | 0 |  |  | 0
1.1.1 | # ASG miners that aligned their policies with the FT/FM in support of women's needs and rights | 15000 | 8654 | 6346
1.1.2 | # ASG miners that adapted operational procedures in line with FT/FM in support of women's needs and rights | 123220 | 48962 | 74258
1.2.1 | Assessments of local and national policies conducted | 21750 | 10631 | 11119
1.2.2 | # local or national gender sensitive ASGM policies being developed | 3625 | 0 | 3625
1.2.3 | # local or national gender sensitive ASGM policies finalised and approved | 11000 | 2662 | 8338
1.3.1 | # of gold buyers with secured sourcing commitments for gold produced in the project | 35500 | 17323 | 18177
1.3.2 | # of market players that have attended meetings or received information about responsible gold in support of women's needs and rights | 12100 | 10050 | 2050
1.4.1 | # of new credit products available to ASG miners | 6387.5 | 6388 | -0.5
1.4.2 | # of ASG miners that use new financial instruments for ASGMS | 6387.5 | 6388 | -0.5
1.1 Gold mines operate according to fair mining practices in support of women's needs and rights |  |  |  | 0 | 0 | 233624 | 143858 | 89766 | 0 | 54533 | 166849 | -112316 | 0 | 64255 | 82976 | -1257 | 0 | 80119 | 64749 | 15370 | 0
1.2 Gender-sensitive ASG mining policies are in place at local and national levels |  |  |  | 0 | 0 | 56004 | 29886 | 26118 | 0 | 51305 | 85393.5 | -34088.5 | 0 | 47258 | 44000.3 | 9605.68 | 0 | 36300 | 29629 | 6671 | 0
1. 3 Market players demand responsible gold in support of women's needs and rights |  |  |  | 0 | 0 | 60850 | 27272.5 | 33577.5 | 0 | 70500 | 16849 | 53651 | 0 | 98815 | 23537 | 77518.5 | 0 | 31055.5 | 69628 | -38572.5 | 0
1.4 ASG mines have access to credit to implement fair mining practices |  |  |  | 0 |  | 12750 | 1796.3 | 10953.7 |  | 21152 | 5340 | 15812 |  | 27253 | 18688 | 9036 |  | -0.5 | 0 | -0.5
1. 5 Women in mines have improved positions | Women in mines have improved positions |  |  | 0 |  | 105150 | 65638 | 39512 |  | 53822 | 56779 | -2957 |  | 28112 | 35737 | -212 |  | 46101 | 38477 | 7624
1.1.0 Objective 1 Supporting costs | Objective 1 Supporting costs | 27560 | 21897.1462 | 5662.8538 |  | 29409 | 23160.5 | 6248.5 |  | 50223.5 | 62470.3566 | -12246.8566 |  | 46632 | 57733.586 | -9616 |  | 51072.6 | 52117 | -1044.4
| TOTAL OUTCOME 1 | 262530 | 132955.1462 | 129574.8538 |  | 497787 | 291611.3 | 206175.7 |  | 301535.5 | 393680.8566 | -92145.3566 |  | 312325 | 262671.886 | 85075.18 |  | 244647.6 | 254600 | -9952.4 |  | 1264762 | 1335519.1888 | -70757.1888 | 105.6%
Outcome 2: Women in mining communities have increased abilities to engage in economic activities |  | 486191 | 240298.96 | 245892.04 |  | 719463.4 | 533853 | 185610.4 |  | 237861.3864 | 294162.52 | -56301.1336 |  | 106800 | 115166.3074 | -8393.94 |  | 108853 | 96075 | 12778
2.1.1 | % of women that have adopted healthier behaviour in their daily lives (use of contraceptives, MHM, ANC,..) | 86000 | 58231.73 | 27768.27
2.1.2 | % of SRH facilities that increased their compliance to the (national) quality standard in the intervention areas | 53000 | 46800 | 6200
2.2.1 | % of women that indicate to have more time available to spend on economic activities | 157500 | 78674.94 | 78825.06
2.2.2 | % community acceptance on women to decide on family planning | 109191 | 47312.29 | 61878.71
2.2.3 | % of women who feel more productive during their periods | 25500 | 9280 | 16220
2.3.1 | Acceptance in the community for women to co-decide on family planning | 35000 | 0 | 35000
2.3.2 | % community leaders that have demonstrated to be supportive to equal opportunities for women | 20000 | 0 | 20000
2.1 Women in mining communities have improved SRHR |  |  |  | 0 |  | 202722 | 148622.0722 | 54099.9278 |  | 72567 | 101736.492 | -29169.492 |  | 31300 | 34084.737 | -4636.4205 |  | 33175 | 29632 | 3543
2.2 Mining communities, especially men, recognise the importance of gender equality |  |  |  | 0 |  | 339921.4 | 266272.9449 | 73648.4551 |  | 56810 | 72526.3156 | -15716.3156 |  | 22966.6667 | 25056.0539 | -3436.2641 |  | 26975 | 23989 | 2986
2.3 Effective national lobby for women-friendly health services | Effective national lobby for women-friendly health services |  |  | 0 |  | 53480 | 31783.3 | 21696.7 |  | 49263.3864 | 27143 | 22120.3864 |  | 13033.3333 | 13475.7899 | 4926.3333 |  | 17728 | 15242 | 2486
2.4 Women have increased access to and control over resources | Women have increased access to and control over resourcess |  |  | 0 |  | 123340 | 87174.6829 | 36165.3171 |  | 59221 | 92756.7125 | -33535.7125 |  | 39500 | 42549.7266 | -5247.5887 |  | 30975 | 27212 | 3763
2.2.0 Objective 2 Supporting costs | Objective 1 Supporting costs | 70800 | 47025.6435 | 23774.3565 |  | 62373 | 61284.67 | 1088.33 |  | 99000 | 81048.51 | 17951.49 |  | 71717 | 82564.914 | -20912 |  | 77103.9 | 78564 | -1460.1
| TOTAL OUTCOME 2 | 556991 | 287324.6035 | 269666.3965 |  | 781836.4 | 595137.67 | 186698.73 |  | 336861.3864 | 375211.03 | -38349.6436 |  | 178517 | 197731.2214 | -29305.94 |  | 185956.9 | 174639 | 11317.9 |  | 1593196 | 1630043.5248 | -36847.5248 | 102.3%
3.1.0 Monitoring and Evaluation |  | 57340 | 37926.55 | 19413.45 |  | 7500 | 35578.5 | -28078.5 |  | 0 | 0 | 0 |  | 47500 | 46818.5 | -235 |  | 56000 | 56172 | -172
3.2.0 PME Supporting costs | M&E including external evaluators / auditors | 19900 | 15140.0865 | 4759.9135 |  | 14694.5 | 27572 | -12877.5 |  | 15832.8815 | 20948 | -5115.1185 |  | 17560 | 18590.4 | 1945 |  | 21651.1722 | 20104 | 1547.1722
| TOTAL PME COSTS | 77240 | 53066.6365 | 24173.3635 |  | 22194.5 | 63150.5 | -40956 |  | 15832.8815 | 20948 | -5115.1185 |  | 65060 | 65408.9 | 1710 |  | 77651.1722 | 76276 | 1375.1722 |  | 225960 | 278850.0365 | -52890.0365 | 123.4%
3.3.0 CSO capacity building |  | 22700 | 11377 | 11323 |  | 24000 | 35535 | -11535 |  | 20500 | 15356.52 | 5143.48 |  | 10500 | 3500 | 6160 |  | 6500 | 5607 | 893 |  |  |  | 0
3.3.1 CSO capacity building supporting costs | M&E including external evaluators / auditors | 22700 | 11377 | 11323 |  | 20374 | 16724.91 | 3649.09 |  | 8653.22 | 9616 | -962.78 |  | 5993 | 6746.4 | -3434 |  | 5065.5088 | 5295 | -229.4912 |  |  |  | 0
| TOTAL CSO CAPACITY BUILDING COSTS | 45400 | 22754 | 22646 |  | 44374 | 52259.91 | -7885.91 |  | 29153.22 | 24972.52 | 4180.7 |  | 16493 | 10246.4 | 2726 |  | 11565.5088 | 10902 | 663.5088 |  | 140585 | 121134.83 | 19450.17 | 86.16%
3.4.0 Programme support The Netherlands | M&E including external evaluators / auditors | 157742 | 121074.11 | 36667.89 |  | 180373.05 | 148481.325 | 31891.725 |  | 163953.7895 | 119570.665 | 44383.1245 |  | 123942 | 121327.585 | 13419 |  | 120864.5672 | 90207 | 30657.5672 |  | 730340 | 600660.685 | 129679.315 | 82.24%
| TOTAL OTHER COSTS | 280382 | 196894.7465 | 83487.2535 |  | 246941.55 | 263891.735 | -16950.185 |  | 208939.891 | 165491.185 | 43448.706 |  | 205495 | 196982.885 | 17855 |  | 210081.2483 | 177385 | 32696.2483 |  | 1096885 | 1000645.5515 | 96239.4485 | 91.23%
[23 empty] | 0 | 0
| GRAND TOTAL | 1099903 | 617174.4962 | 482728.5038 |  | 1526564.95 | 1150640.705 | 375924.245 |  | 847336.7774 | 934383.0717 | -87046.2943 |  | 696337 | 657385.9924 | 73624.24 |  | 640685.7483 | 606624 | 34061.7483 |  | 3954843 | 3966208.2652 | -11365.2652 | 100.3%

## Liquidity Overview
Liquidity overview
installments 2016 | 2236986
installments dec 2016 | 800000
installments jan 2017 | 1393721
installment Dec 2017 | 1350964
Installment April 2019 | 1086206
Installment January 2020 | 727855
Total Disbursements 2016-2020 | 7595732
Expenditures 2016 | 1310261
Expenditures 2017 | 2487226
Expenditures 2018 | 1617726
Expenditures 2019 | 1285865.1578
Expenditures 2020 | 1285214.962
TOTAL | 7986293.1198
Expected Funds available 2021 | 399775.1544
Actual Funds Request 2021 | 390432.9678